## PROGRESSION
GELARAN MAJU SDN BHD
PROJECT: THE CAPITOL / MSK
Report Date: 12 SEPTEMBER 2026
LEVEL |  | COLD WATER |  |  |  | 47.61% |  |  | SANITARY |  | 47.02% |  |  | IRRIGATION |  | 6.125% |  | SUPAHAM | LEADER | ASSISTANT
|  | PIPE SLEEVE | PUMP | PUMP CONTROL PANEL | TRANSFER PUMP PIPES | L31 & 31M ROOF PIPING | CW TENANT | BACKSHAFT CW & FW TOILETS | HOSEREEL FLOORTRAP & STACK | SANITARY TENANT | TOILET PIPE DISTRIBUTION & HACKING | SANITARY TOILETS | SANITARY WARES INSTALLATION | IRRIGATION OUTLET | IRRIGATION INLET | IRRIGATION WIRING | IRRIGATION CONTROL PANEL | team 1 | SOLIHIN | ASHRAFUL | JIARUL | YASIN
13 | TOWER A | 100% | N/A | N/A | 95% | N/A | 95% | 0% | 95% | 95% | 0% | 0% | 0% | 100% | 90% | 0% | N/A | team 2 | ASGAR | RANA
14 |  | 100% |  |  | 95% |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 100% | 0% | 0% |  | team 3 | SUHAIRI | SUPENDI
15 |  | 100% |  |  | 95% |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 0% | 0% |  | team 4 | BILAL | FARHAD | SOFIKUL | SYAHIB | AMIRUL | NURUL | NAZMUL
16 |  | 100% |  |  | 95% |  | 95% | 95% | 50% | 50% | 100% | 95% | 95% | 95% | 0% | 0% |  | team 5 | JUWEL | BADOL
17 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 100% | 95% | 10% | 0% | 0% | 0% |  | team 6 | JILLUR | ISLAM
18 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 100% | 95% | 0% | 10% | 0% | 0% |  | team 7 | SARIP | SYAHIB
19 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 100% | 95% | 0% | 0% | 0% | 0% |  | team 8 | EMON | MAHMUD
20 |  | 100% |  |  | 95% |  | 95% | 0% | 95% | 95% | 20% | 95% | 0% | 0% | 0% | 0% |  | team 9 | IBNU | DAMIL
21 |  | 100% |  |  | 95% |  | 95% | 0% | 95% | 95% | 0% | 95% | 0% | 0% | 0% | 0% |  | team 10 | KAMAL
22 |  | 100% |  |  | 95% |  | 95% | 0% | 95% | 95% | 95% | 95% | 0% | 0% | 0% | 0% | 0%
23 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 0% | 95% | 0% | 0% | 0% | 0% | N/A
24 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 0% | 95% | 0% | 0% | 0% | 0%
25 |  | 100% |  |  | 95% |  | 95% | 0% | 95% | 95% | 0% | 95% | 0% | 0% | 0% | 0%
26 |  | 100% |  |  | 95% |  | 95% | 0% | 95% | 95% | 95% | 95% | 0% | 0% | 0% | 0%
27 |  | 100% |  |  | 95% |  | 95% | 0% | 95% | 95% | 0% | 95% | 0% | 0% | 0% | 0%
28 |  | 100% |  |  | 95% |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29 |  | 100% |  |  | 0% |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30 |  | 100% |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31 |  | 55% | 95% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31M |  | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | TOWER B | 100% | N/A | N/A | 95% | N/A | 95% | 0% | 95% | 95% | 0% | 0% | 0% | 100% | 90% | 0% | N/A
14 |  | 100% |  |  | 95% |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 100% | 0% | 0%
15 |  | 100% |  |  | 95% |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 0% | 0%
16 |  | 100% |  |  | 95% |  | 95% | 10% | 50% | 50% | 95% | 95% | 95% | 95% | 0% | 0%
17 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 95% | 95% | 10% | 0% | 0% | 0%
18 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 95% | 95% | 0% | 10% | 0% | 0%
19 |  | 100% |  |  | 95% |  | 95% | 0% | 50% | 50% | 95% | 95% | 0% | 0% | 0% | 0%
20 |  | 100% |  |  | 0% |  | 95% | 0% | 95% | 95% | 20% | 95% | 0% | 0% | 0% | 0%
21 |  | 100% |  |  | 0% |  | 95% | 0% | 95% | 95% | 0% | 95% | 0% | 0% | 0% | 0%
22 |  | 100% |  |  | 0% |  | 95% | 0% | 95% | 95% | 95% | 95% | 0% | 0% | 0% | 0% | 0%
23 |  | 100% |  |  | 0% |  | 95% | 0% | 50% | 50% | 0% | 95% | 0% | 0% | 0% | 0% | N/A
24 |  | 100% |  |  | 0% |  | 95% | 0% | 50% | 50% | 0% | 50% | 0% | 0% | 0% | 0%
25 |  | 100% |  |  | 0% |  | 95% | 0% | 95% | 95% | 0% | 95% | 0% | 0% | 0% | 0%
26 |  | 100% |  |  | 0% |  | 95% | 0% | 95% | 95% | 95% | 95% | 0% | 0% | 0% | 0%
27 |  | 100% |  |  | 0% |  | 95% | 0% | 95% | 95% | 0% | 95% | 0% | 0% | 0% | 0%
28 |  | 100% |  |  | 0% |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29 |  | 100% |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30 |  | 100% |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31 |  | 50% | 95% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31M |  | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 93.13% | 47.5% | 47.5% | 54.62% | 0% | 78.37% | 12.12% | 57.75% | 57.75% | 39.5% | 65.37% | 14.75% | 20% | 4.5% | 0% | 0%

## COMPARE
Tower A vs Tower B ¦ % complete
Tower A leads overall by 3.5%
PACKAGE |  | Tower A | Tower B | Gap (A−B) | Leader
COLD WATER |  | 51.32% | 43.89% | 7.429% | Tower A
SANITARY |  | 47.35% | 46.7% | 0.65% | Tower A
IRRIGATION |  | 6.125% | 6.125% | 0% | Tie
OVERALL |  | 38.78% | 35.33% | 3.453% | Tower A
PACKAGE | Item | Tower A | Tower B | Gap (A−B) | Leader
Cold Water | Pipe Sleeve | 93.25% | 93% | 0.25% | Tower A
Cold Water | Pump | 47.5% | 47.5% | 0% | Tie
Cold Water | Pump Control Panel | 47.5% | 47.5% | 0% | Tie
Cold Water | Transfer Pump Pipes | 76% | 33.25% | 42.75% | Tower A
Cold Water | L31 & 31M Roof Piping | 0% | 0% | 0% | Tie
Cold Water | CW Tenant | 80.75% | 76% | 4.75% | Tower A
Cold Water | Backshaft CW & FW Toilets | 14.25% | 10% | 4.25% | Tower A
Sanitary | Hosereel Floortrap & Stack | 57.75% | 57.75% | 0% | Tie
Sanitary | Sanitary Tenant | 57.75% | 57.75% | 0% | Tie
Sanitary | Toilet Pipe Distribution & Hacking | 40% | 39% | 1% | Tower A
Sanitary | Sanitary Toilets | 66.5% | 64.25% | 2.25% | Tower A
Sanitary | Sanitary Wares Installation | 14.75% | 14.75% | 0% | Tie
Irrigation | Irrigation Outlet | 20% | 20% | 0% | Tie
Irrigation | Irrigation Inlet | 4.5% | 4.5% | 0% | Tie
Irrigation | Irrigation Wiring | 0% | 0% | 0% | Tie
Irrigation | Irrigation Control Panel | 0% | 0% | 0% | Tie

## ORDER
Material Order ¦ qty
Report Date: 12 SEPTEMBER 2026 · Blue = qty/floor and ordered
Package | Material | Unit | Qty / floor | Remaining A | Remaining B | Required | Ordered | Balance | Status | Remarks | Package | Required | Ordered | Balance
Cold Water | Pipe sleeve | nos | 1 | 1.35 | 1.4 | 2.75 | 0 | 2.75 | To Order |  | Cold Water | 72.9 | 0 | 72.9
Cold Water | Transfer pump pipes | floor | 1 | 4.8 | 13.35 | 18.15 | 0 | 18.15 | To Order |  | Sanitary | 405.7 | 0 | 405.7
Cold Water | CW tenant pipework | floor | 1 | 3.85 | 4.8 | 8.65 | 0 | 8.65 | To Order |  | Irrigation | 114.2 | 0 | 114.2
Cold Water | Backshaft CW & FW pipe | floor | 1 | 17.15 | 18 | 35.15 | 0 | 35.15 | To Order |  | TOTAL | 592.8 | 0 | 592.8
Cold Water | L31 & 31M roof piping | lot | 1 | 2 | 2 | 4 | 0 | 4 | To Order
Cold Water | Pump | set | 1 | 1.05 | 1.05 | 2.1 | 0 | 2.1 | To Order
Cold Water | Pump control panel | set | 1 | 1.05 | 1.05 | 2.1 | 0 | 2.1 | To Order
Sanitary | Hosereel set | nos | 6 | 8.45 | 8.45 | 101.4 | 0 | 101.4 | To Order
Sanitary | Floor trap | nos | 6 | 8.45 | 8.45 | 101.4 | 0 | 101.4 | To Order
Sanitary | Sanitary stack pipe | floor | 1 | 8.45 | 8.45 | 16.9 | 0 | 16.9 | To Order
Sanitary | Toilet distribution pipe | floor | 1 | 12 | 12.2 | 24.2 | 0 | 24.2 | To Order
Sanitary | Sanitary tenant | floor | 1 | 8.45 | 8.45 | 16.9 | 0 | 16.9 | To Order
Sanitary | WC pan | nos | 4 | 6.7 | 7.15 | 55.4 | 0 | 55.4 | To Order
Sanitary | Wash basin | nos | 4 | 6.7 | 7.15 | 55.4 | 0 | 55.4 | To Order
Sanitary | Sanitary wares | floor | 1 | 17.05 | 17.05 | 34.1 | 0 | 34.1 | To Order
Irrigation | Irrigation outlet | nos | 1 | 16 | 16 | 32 | 0 | 32 | To Order
Irrigation | Irrigation inlet | nos | 1 | 19.1 | 19.1 | 38.2 | 0 | 38.2 | To Order
Irrigation | Irrigation cable | floor | 1 | 20 | 20 | 40 | 0 | 40 | To Order
Irrigation | Irrigation control panel | set | 1 | 2 | 2 | 4 | 0 | 4 | To Order
TOTAL |  |  |  | 164.6 | 176.1 | 592.8 | 0 | 592.8

## FLOORS
Floor-by-floor ¦ % complete
A ahead 15 · B ahead 0 · tie 5
Level | Tower A | Tower B | Gap (A−B) | Leader
13 | 55.83% | 55.83% | 0% | Tie
14 | 80% | 80% | 0% | Tie
15 | 79.58% | 79.58% | 0% | Tie
16 | 72.5% | 65% | 7.5% | Tower A
17 | 49.58% | 49.17% | 0.4167% | Tower A
18 | 49.58% | 49.17% | 0.4167% | Tower A
19 | 48.75% | 48.33% | 0.4167% | Tower A
20 | 49.58% | 41.67% | 7.917% | Tower A
21 | 47.92% | 40% | 7.917% | Tower A
22 | 51.54% | 44.23% | 7.308% | Tower A
23 | 40.42% | 32.5% | 7.917% | Tower A
24 | 40.42% | 28.75% | 11.67% | Tower A
25 | 47.92% | 40% | 7.917% | Tower A
26 | 55.83% | 47.92% | 7.917% | Tower A
27 | 47.92% | 40% | 7.917% | Tower A
28 | 24.17% | 16.25% | 7.917% | Tower A
29 | 16.25% | 8.333% | 7.917% | Tower A
30 | 8.333% | 8.333% | 0% | Tie
31 | 16.33% | 16% | 0.3333% | Tower A
31M | 0.625% | 0.625% | 0% | Tie
OVERALL | 44.15% | 39.58% | 4.57% | Tower A

## SITE REPORT
Site report ¦ % complete
Report Date: 12 SEPTEMBER 2026
Overall | Cold Water | Sanitary | Irrigation | Men | Day RM
33.59% | 47.61% | 47.02% | 6.125% | 27 | 15900
Weather | Fair | Shift | Day
Today | Transfer pump + hosereel
Blockers
Tomorrow
Item | Progress | Status | Owner
PIPE SLEEVE | 93.12% | Complete
PUMP | 47.5% | In Progress
PUMP CONTROL PANEL | 47.5% | In Progress
TRANSFER PUMP PIPES | 54.62% | In Progress
L31 & 31M ROOF PIPING | 0% | Not Started
CW TENANT | 78.38% | In Progress
BACKSHAFT CW & FW TOILETS | 12.12% | In Progress
HOSEREEL FLOORTRAP & STACK | 57.75% | In Progress
SANITARY TENANT | 57.75% | In Progress
TOILET PIPE DISTRIBUTION & HACKING | 39.5% | In Progress
SANITARY TOILETS | 65.38% | In Progress
SANITARY WARES INSTALLATION | 14.75% | In Progress
IRRIGATION OUTLET | 20% | In Progress
IRRIGATION INLET | 4.5% | In Progress
IRRIGATION WIRING | 0% | Not Started
IRRIGATION CONTROL PANEL | 0% | Not Started

## PO LOG
PO log ¦ RM
Report Date: 12 SEPTEMBER 2026
Date | PO No | Material | Supplier | Qty | Unit | Amount RM | Status | ETA | Remarks | Still to order | Lines
[10 empty] | To Order | 19
[10 empty] | Partial | 0
[10 empty] | Complete | 0
TOTAL |  |  |  | 0 |  | 0 | 0 POs

## MANPOWER
Manpower vs progress
Report Date: 12 SEPTEMBER 2026
On site | Day RM | Overall | RM / 1% | Package | Progress | Remaining
27 | 15900 | 33.59% | 473.4156 | Cold Water | 47.61% | 52.39%
|  |  |  | Sanitary | 47.02% | 52.98%
Name | Rate RM | On site | Cost today | Irrigation | 6.125% | 93.88%
SUPAHAM | 2000 | 1 | 2000
SOLIHIN | 1000 | 1 | 1000
ASGAR | 500 | 1 | 500
SUHAIRI | 700 | 1 | 700
BILAL | 500 | 1 | 500
JUWEL | 500 | 1 | 500
JILLUR | 500 | 1 | 500
SARIP | 700 | 1 | 700
EMON | 500 | 1 | 500
IBNU | 500 | 1 | 500
KAMAL | 500 | 1 | 500
YASIN | 500 | 1 | 500
SOFIKUL | 1000 | 1 | 1000
NAZMUL | 500 | 1 | 500
MAHMUD | 500 | 1 | 500
NURUL | 500 | 1 | 500
JIARUL | n/a | 1 | 0
SUPENDI | 500 | 1 | 500
RANA | 500 | 1 | 500
ASHRAFUL | 500 | 1 | 500
FARHAD | 500 | 1 | 500
BADOL | 500 | 1 | 500
ISLAM | 500 | 1 | 500
SYAHIB | 500 | 1 | 500
AMIRUL | 500 | 1 | 500
DAMIL | 500 | 1 | 500
KAMAL | 500 | 1 | 500
TOTAL |  | 27 | 15900

## ATTENDANCE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SUPAHAM
SOLIHIN
ASGAR
SUHAIRI
BILAL
JUWEL
JILLUR
SARIP
EMON
IBNU
KAMAL
YASIN
SOFIKUL
NAZMUL
MAHMUD
NURUL
JIARUL
SUPENDI
RANA
ASHRAFUL
FARHAD
BADOL
ISLAM
SYAHIB
AMIRUL
DAMIL
KAMAL

## aipoon
Bill Of Quantities
RE: | UPVC PIPE FOR TOILET, TENANT AND HOSEREEL FOR LEVEL 24- LEVEL 31 @ MSK
ITEM | DESCRIPTION | QUANTITY/UNIT |  | UNIT RATE (RM) | PREVIOUS CLAIM (%) | WORK DONE (%) | AMOUNT | SIGN / VERIFY
A | SANITARY SERVICES
1 | TOILET HIGH LEVEL AND DROPPER TOWER A & B (4SET OF TOILET) AT L25-L31
1.1 | To install UPVC pipe waste and vent pipes and vertical stack including all fittings, cleaning eyes, brackets, bends, joints, flexible joints, vent cowl, traps, floor traps, floor outlet, brackets, hangers, off-sets, supports, etc
| LEVEL 25 | Lot | 1 | 5800 | 0% | 95% | 5510
| LEVEL 26 | Lot | 1 | 5800 | 0% | 0% | 0
| LEVEL 27 | Lot | 1 | 5800 | 0% | 95% | 5510
| LEVEL 28 | Lot | 1 | 5800 | 0% | 0% | 0
| LEVEL 29 | Lot | 1 | 5800 | 0% | 0% | 0
| LEVEL 30 | Lot | 1 | 5800 | 0% | 0% | 0
| LEVEL 31 | Lot | 1 | 2900 | 0% | 0% | 0
2 | TENANT OUTLET AND DROPPER TOWER A & B AT L25-L31
2.1 | To install UPVC pipe waste and vent pipes and vertical stack including all fittings, cleaning eyes, brackets, bends, joints, flexible joints, vent cowl, traps, floor traps, floor outlet, brackets, hangers, off-sets, supports, etc
| LEVEL 25 | Lot | 1 | 1600 | 0% | 95% | 1520
| LEVEL 26 | Lot | 1 | 1600 | 0% | 0% | 0
| LEVEL 27 | Lot | 1 | 1600 | 0% | 95% | 1520
| LEVEL 28 | Lot | 1 | 1600 | 0% | 0% | 0
| LEVEL 29 | Lot | 1 | 1600 | 0% | 0% | 0
| LEVEL 30 | Lot | 1 | 1600 | 0% | 0% | 0
| LEVEL 31 | Lot | 1 | 1600 | 0% | 0% | 0
3 | HOSEREEL OUTLET AND DROPPER TOWER A & B AT L25-L31
3.1 | To install UPVC pipe waste and vent pipes and vertical stack including all fittings, cleaning eyes, brackets, bends, joints, flexible joints, vent cowl, traps, floor traps, floor outlet, brackets, hangers, off-sets, supports, etc
| LEVEL 25 | Lot | 1 | 510 | 0% | 95% | 484.5
| LEVEL 26 | Lot | 1 | 510 | 0% | 0% | 0
| LEVEL 27 | Lot | 1 | 510 | 0% | 95% | 484.5
| LEVEL 28 | Lot | 1 | 510 | 0% | 0% | 0
| LEVEL 29 | Lot | 1 | 510 | 0% | 0% | 0
| LEVEL 30 | Lot | 1 | 510 | 0% | 0% | 0
| LEVEL 31 | Lot | 1 | 510 | 0% | 0% | 0
4 | ADDITIONAL
TOILET HIGH LEVEL AND DROPPER TOWER A&B (2SET OF TOILET) AT L24
| LEVEL 24 TOWER B | Lot | 1 | 2900 | 0% | 0% | 0
| LEVEL 24 TOWER A (BRICKWALL) | Lot | 1 | 2900 | 0% | 0% | 0
| TOTAL AMOUNT |  |  | 58270 |  |  | 15029
VERIFICATION
Prepared by |  |  | Checked by |  |  | Verified / Approved
Sign: |  |  | Sign: |  |  | Sign:
Name: ALVIN |  |  | Name: KHAIRUL |  |  | Name: AH FATT
Date: |  |  | Date: |  |  | Date:

## ariyan
Bill Of Quantities
RE: | STAINLESS STEEL TRANSFER PUMP PIPE ¦ TOWER A AND TOWER B @ MSK
RATE: RM 80 PER METER, ADDITIONAL FITTINGS RM 150 PER NO. (ELBOW / CHECK VALVE), RM 80 PER SAMPLING POINT
ITEM | DESCRIPTION | QUANTITY/UNIT |  | UNIT RATE (RM) | PREVIOUS CLAIM (%) | WORK DONE (%) | AMOUNT | SIGN / VERIFY
A | WORKER LABOUR
1.0 | TOWER A ¦ STAINLESS STEEL TRANSFER PUMP PIPE
1.1 | To install stainless steel transfer pump pipe
| LEVEL 13 | m | 10.75 | 80 | 0% | 95% | 817
| LEVEL 14 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 15 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 16 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 17 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 18 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 19 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 20 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 21 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 22 | m | 4.5 | 80 | 0% | 0% | 0
| LEVEL 23 | m | 4.5 | 80 | 0% | 0% | 0
| LEVEL 24 | m | 4.5 | 80 | 0% | 0% | 0
| LEVEL 25 | m | 4.5 | 80 | 0% | 0% | 0
| LEVEL 26 | m | 4.5 | 80 | 0% | 0% | 0
| LEVEL 27 | m | 5.1 | 80 | 0% | 0% | 0
| LEVEL 28 | m | 5.1 | 80 | 0% | 0% | 0
| LEVEL 29 | m | 5.1 | 80 | 0% | 0% | 0
| LEVEL 30 | m | 6 | 80 | 0% | 0% | 0
| LEVEL 31 | m | 12.7 | 80 | 0% | 0% | 0
1.2 | Additional fittings. Rate RM150 per no. (elbow / check valve).
| LEVEL 13 ¦ ELBOW | NOS | 3 | 150 | 0% | 95% | 427.5
| LEVEL 14 ¦ ELBOW / CHECK VALVE | NOS | 2 | 150 | 0% | 95% | 285
| LEVEL 21 ¦ ELBOW | NOS | 2 | 150 | 0% | 0% | 0
| LEVEL 23 ¦ CHECK VALVE | NOS | 1 | 150 | 0% | 0% | 0
| LEVEL 13 ¦ SAMPLING POINT | NOS | 1 | 80 | 0% | 100% | 80
| LEVEL 23 ¦ SAMPLING POINT | NOS | 1 | 80 | 0% | 0% | 0
2.0 | TOWER B ¦ STAINLESS STEEL TRANSFER PUMP PIPE
2.1 | To install stainless steel transfer pump pipe
| LEVEL 21 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 22 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 23 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 24 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 25 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 26 | m | 4.5 | 80 | 0% | 95% | 342
| LEVEL 27 | m | 5.1 | 80 | 0% | 95% | 387.6
| LEVEL 28 | m | 5.1 | 80 | 0% | 95% | 387.6
| LEVEL 29 | m | 5.1 | 80 | 0% | 95% | 387.6
| LEVEL 30 | m | 6 | 80 | 0% | 0% | 0
| LEVEL 31 | m | 12.7 | 80 | 0% | 0% | 0
2.2 | Additional fittings. Rate RM150 per no. (elbow / check valve).
| LEVEL 23 ¦ CHECK VALVE | NOS | 1 | 150 | 0% | 0% | 0
| LEVEL 13 ¦ SAMPLING POINT | NOS | 1 | 80 | 0% | 0% | 0
| LEVEL 23 ¦ SAMPLING POINT | NOS | 1 | 80 | 0% | 0% | 0
| TOTAL AMOUNT |  |  | 14810 |  |  | 7560.3

## Sheet2
GM |  |  | SUBS
1 | SUPAHAM | 2000 | 1 | AIPOON | 0
2 | SOLIHIN | 1000 | 2 | WELDER
3 | ASGAR | 500
4 | SUHAIRI | 700
5 | BILAL | 500
6 | JUWEL | 500
7 | JILLUR | 500
8 | SARIP | 700
9 | EMON | 500
10 | IBNU | 500
11 | KAMAL | 500
12 | YASIN | 500
13 | SOFIKUL | 1000
14 | NAZMUL | 500
15 | MAHMUD | 500
16 | NURUL | 500
17 | JIARUL | n/a
18 | SUPENDI | 500
19 | RANA | 500
20 | ASHRAFUL | 500
21 | FARHAD | 500
22 | BADOL | 500
23 | ISLAM | 500
24 | SYAHIB | 500
25 | AMIRUL | 500
26 | DAMIL | 500
27 | KAMAL | 500
| TOTAL | 15900